## Slide 1: Scrum
An introduction

## Slide 2: What is Scrum?
Scrum:
  Is an agile, lightweight process
  Can manage and control software and product development
  Uses iterative, incremental practices
  Has a simple implementation
  Increases productivity
  Reduces time to benefits
  Embraces adaptive, empirical systems development
  Is not restricted to software development projects
  Embraces the opposite of the waterfall approach…

## Slide 3: Scrum Origins
Jeff Sutherland
  Initial scrums at Easel Corp in 1993
  IDX and 500+ people doing Scrum
Ken Schwaber
  ADM
  Scrum presented at OOPSLA 96 with Sutherland
  Author of three books on Scrum
Mike Beedle
  Scrum patterns in PLOPD4
Ken Schwaber and Mike Cohn
  Co-founded Scrum Alliance in 2002, initially within Agile Alliance

## Slide 4: Agile Manifesto
Process and tools
Individuals and interactions
over
Following a plan
Responding to change
over
Source: www.agilemanifesto.org
Comprehensive documentation
Working software
over
Contract negotiation
Customer collaboration
over

## Slide 5: Scrum at a Glance
30 days
24 hours
Product Backlog
As prioritized by Product Owner
Sprint Backlog
Backlog tasks
expanded
by team
Potentially Shippable
Product Increment
Daily Scrum
Meeting
Source: Adapted from Agile Software Development with Scrum by Ken Schwaber and Mike Beedle.
There are variations of scrum –some companies do weekly or every X day meetings
How many lines of code on average do you think a Google SW Engineer produces?

## Slide 6: Sequential vs. Overlap
Rather than doing all of one thing at a time...
...Scrum teams do a little of everything all the time
Requirements
Design
Code
Test

## Slide 7: Scrum Framework
Product owner
Scrum Master
Team
Roles
Ceremonies
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting
Product backlog
Sprint backlog
Burndown charts
Artifacts

## Slide 8: Scrum Roles
  Product Owner
    Possibly a Product Manager or Project Sponsor
    Decides features, release date, prioritization, $$$
  Scrum Master
    Typically a Project Manager or Team Leader
    Responsible for enacting Scrum values and practices
    Remove impediments / politics, keeps everyone productive
  Project Team
    5-10 members; Teams are self-organizing
    Cross-functional: QA, Programmers, UI Designers, etc.
    Membership should change only between sprints

## Slide 9: Importance of different team members "Pigs" and "Chickens"
Pig: Team member committed to success of project
Chicken: Not a pig; interested but not committed
A pig and a chicken are walking down a road. The chicken looks at the pig and says, "Hey, why don't we open a restaurant?" The pig looks back at the chicken and says, "Good idea, what do you want to call it?" The chicken thinks about it and says, "Why don't we call it 'Ham and Eggs'?" "I don't think so," says the pig, "I'd be committed but you'd only be involved."
SCRUM: chickens have input on the product that will be developed, but pigs decide how it’s going to be done and the rate at which it can be accomplished.
PIG = development team members, product owner who represents the chickens, and the Scrum Master, responsible for organizing a sort of Scrum events especially during Scrum stand-ups.
CHICKENS = customer, vendor, executives and other important people with vision

## Slide 10: What is a Scrum Sprint
30 days
24 hours
Product Backlog
As prioritized by Product Owner
Sprint Backlog
ToDo tasks
Potentially Shippable
Product Increment
Daily Scrum
Meeting
Source: Adapted from Agile Software Development with Scrum by Ken Schwaber and Mike Beedle.
Scrum Sprint is a repeatable fixed time-box during which a "Done" product of the highest possible value is created.

## Slide 11: What Happens in a Scrum Sprint
Scrum Sprint is a repeatable fixed time-box during which a "Done" product of the highest possible value is created.

## Slide 12: Sprint Planning Meeting
Sprint planning meeting
Business conditions
Team capacity
Product backlog
Technology
Current product
Sprint prioritization
Analyze/evaluate product backlog
Select sprint goal (and issues to work on)
Sprint planning
Decide how to achieve sprint goal (design)
Create sprint tasks/issues (sometimes called sprint backlog) from product backlog items (user stories / features)
Estimate sprint backlog in hours
Sprint
goal
Sprint
Backlog

## Slide 13: Daily Scrum Meeting
Parameters
  Daily, ~15 minutes, Stand-up
  Anyone late pays a $1 fee
Not for problem solving
  Whole world is invited
  Only team members, Scrum Master, product owner, can talk
  Helps avoid other unnecessary meetings
3 questions answered by each team member:
  What did you do yesterday?
  What will you do today?
  What obstacles are in your way?
it’s the perfect occasion to share an issue or ask for help. But don’t you try resolving it then.
You do technical discussions/solution brainstorming AFTER the meeting
Notes: 13

## Slide 14: What is that chart in the background at the daily scrum standup?
Like our Kanban Board (we using Trello.com)
So have meeting in same place each day.

## Slide 15: Don’t solve the problem in the Daily Scrum  but people volunteer to assist

## Slide 16: Scrum “Documents” include
Scrum has remarkably few documents
  Kanban type Board / Issues
  Backlog
  Burndown Charts Velocity Chart
Can be managed using just an Excel spreadsheet OR Professional Software
30 days
24 hours
Product Backlog
As prioritized by Product Owner
Sprint Backlog
ToDo
Potentially Shippable
Product Increment
Daily Scrum
Meeting

## Slide 17: Issues Board
Can create Milestones, Assign issues to team members, associate dependencies, associate with releases and more
Below is example of using ZenHub a plugin to GitHub (free for basic use)

## Slide 18: To Do/In Progress (lists in board)
The CURRENT (scrum cycle) requirements  in the To Do / In Progress Lists
A list of all desired work on project for current cycle (or possibly listed for release)
Possibly prioritized
CURRENT issues
ZenHub
Milestone = has 1 or usually multiple issues and theoretically in ZenHub is like a Sprint

## Slide 19: Product Backlog (list in board)
The FUTURE / NEXT set of (scrum cycle) requirements
A list of all desired work on project
Reprioritized at start of each sprint and moved into In Progress list
product backlog

## Slide 20: “User Stories” – concept “Issues,Epics” – in practice
Instead of Use Cases, Agile project owners do "user stories"
  Who (user role) – Is this a customer, employee, admin, etc.?
  What (goal) – What functionality must be achieved/developed?
  Why (reason) – Why does user want to accomplish this goal?
As a [user role], I want to [goal], so I can [reason].
Example:
  "As a user, I want to log in, so I can access subscriber content."
story points: Rating of effort needed to implement this story
  common scales: 1-10, shirt sizes (XS, S, M, L, XL), etc.
  ZenHub: IN PRACTICE these become tasks/ISSUES on our board

## Slide 21: A different Sample Product Backlog
Backlog item | Estimate
Allow a guest to make a reservation | 4 (days)
As a guest, I want to cancel a reservation. | 5
As a guest, I want to change the dates of a reservation. | 3
As a hotel employee, I can run RevPAR reports (revenue-per-available-room) | 8
Improve exception handling | 8
... | 30
... | 50
Notes: 21

## Slide 22: Backlog
Individuals sign up for work of their own choosing
  Work is never assigned
Estimated work remaining is updated daily
Any team member can add, delete change sprint backlog
Work for the sprint emerges
If work is unclear, define a sprint backlog item with a larger amount of time and break it down later
Update work remaining as more becomes known

## Slide 23: Sample Sprint backlog ESTIMATES evolution over time…..
Tasks
Code the user interface
Code the middle tier
Test the middle tier
Write online help
Write the Foo class
Mon
8
16
8
12
8
Tue
4
12
16
8
Wed
Thu
4
11
8
4
Fri
8
8
Add error logging
8
10
16
8
8
The units are typically days but, you can decide as a team what to make them
Notes: 23

## Slide 24: Sprint Burndown Chart
A display of what work has been completed and what is left to complete
  one for each developer or work item
  updated every day
  (make best guess about hours/points completed each day)
variation: Release burndown chart
  shows overall progress
  updated at end of each sprint (called a Milestone in ZenHub)

## Slide 25: Example ZenHub BurnDown chart
Associated with COMPLETED (CLOSED) Milestone
Milestone has start and end date and one or more issues associated with it
For a Milestone to be closed ALL issues associated with it must be closed
A Milestone in ZenHub = 1 Sprint

## Slide 26: ZenHub  FYI what you see for BurnDown chart BEFORE milestone closed
Just projected date of completion and current issues related to it

## Slide 27: A different Sample Burndown Chart
Hours
Notes: 27

## Slide 28
Hours
40
30
20
10
0
Mon
Tue
Wed
Thu
Fri
Tasks
Code the user interface
Code the middle tier
Test the middle tier
Write online help
Mon
8
16
8
12
Tue
Wed
Thu
Fri
4
12
16
7
11
8
10
16
8
50
Notes: 28

## Slide 29: Burndown Example 1 --interpretation
No work being performed

## Slide 30: Burndown Example 2 -- interpretation
Work being performed, but not fast enough

## Slide 31: Burndown Example 3-- interpretation
Work being performed, but too fast!

## Slide 32: Sprint Velocity Chart
Calculate the average speed of work across previously completed Milestones to make accurate commitments each sprint.
ZenHub example for our toy HelloWorld_CS401_Gradle project (and github repository and workspace)

## Slide 33: The Sprint Review
Team presents what it accomplished during the sprint
Typically takes the form of a demo of new features or underlying architecture
Informal
  2-hour prep time rule
  No slides
Whole team participates
Invite the world

## Slide 34: The Sprint Retrospective Meeting
done at the end of a sprint.
reflect on what went well and what didn't go well in the previous sprint and determine how it can be improved in the next sprint.
HUH? Sprint Review is focused on the product and maximizing the business value of the results of the work of the previous sprint and the Sprint Retrospective is focused on the process and continuous process improvement.

## Slide 35: Scalability
Typical individual team is 7 ± 2 people
  Scalability comes from teams of teams
Factors in scaling
  Type of application
  Team size
  Team dispersion
  Project duration
Scrum has been used on multiple 500+ person projects

## Slide 36: Scaling: Scrum of Scrums